## Gantt
Test
Client | Awesome Client
Range | 2026-09-01 | 2026-11-30
Scale | Days | Weekends | Hidden
Legend | Macro / aggregate | Planned activity | To schedule
Activity | Macro | Start | End | Status | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30
Analysis and documentation |  | 2026-09-03 | 2026-09-11 | Aggregate
Functional Analysis | Analysis and documentation | 2026-09-03 | 2026-09-07 | Planned
Call with clients | Analysis and documentation | 2026-09-05 | 2026-09-11 | Planned
Technical Analysis | Analysis and documentation | 2026-09-07 | 2026-09-09 | Planned
Development |  | 2026-09-12 | 2026-09-18 | Aggregate
Front-end | Development | 2026-09-14 | 2026-09-18 | Planned
Back-end | Development | 2026-09-12 | 2026-09-16 | Planned
Test |  | 2026-09-19 | 2026-09-23 | Planned
Validation |  | 2026-09-24 | 2026-09-25 | Planned
Release and monitoring |  | 2026-09-26 | 2026-10-01 | Planned