## Estimate
Title | Test
Client | Awesome Client
Unit | hours
Hours / day | 8
Contingency % | 20
Name | Category | Hours | Days | CTG (h) | CTG (D) | With CTG (h) | With CTG (D) | Presented (h) | Presented (D) | Notes
Analysis and documentation | Analysis | 12 | 1.5 | 2.4 | 0.3 | 14.4 | 1.8 | 14.4 | 1.8
Functional Analysis | Analysis | 2 | 0.25 | 0.4 | 0.05 | 2.4 | 0.3 | 2.4 | 0.3
Call with clients | Analysis | 6 | 0.75 | 1.2 | 0.15 | 7.2 | 0.9 | 7.2 | 0.9
Technical Analysis | Analysis | 4 | 0.5 | 0.8 | 0.1 | 4.8 | 0.6 | 4.8 | 0.6
Development | Development | 14 | 1.75 | 2.8 | 0.35 | 16.8 | 2.1 | 16.8 | 2.1
Front-end | Development | 10 | 1.25 | 2 | 0.25 | 12 | 1.5 | 12 | 1.5
Back-end | Development | 4 | 0.5 | 0.8 | 0.1 | 4.8 | 0.6 | 4.8 | 0.6
Test | Test | 4 | 0.5 | 0.8 | 0.1 | 4.8 | 0.6 | 4.8 | 0.6
Validation | Validation | 2 | 0.25 | 0.4 | 0.05 | 2.4 | 0.3 | 2.4 | 0.3
Release and monitoring | Release | 4 | 0.5 | 0.8 | 0.1 | 4.8 | 0.6 | 4.8 | 0.6
Project Management | PM | 3.6 | 0.45 | 0 | 0 | 3.6 | 0.45 | 3.6 | 0.45
Total base (h) | 39.6 | Total base (D) | 4.95
Total CTG (h) | 7.2 | Total CTG (D) | 0.9
Total with CTG (h) | 46.8 | Total with CTG (D) | 5.85
Total presented (h) | 46.8 | Total presented (D) | 5.85