## Estimate
Title | New estimate, client 1
Client
Unit | hours
Hours / day | 8
Contingency % | 20
Name | Category | Hours | Days | CTG (h) | CTG (D) | With CTG (h) | With CTG (D) | Presented (h) | Presented (D) | Notes
Analysis and documentation | Analysis | 14 | 1.75 | 2.8 | 0.35 | 16.8 | 2.1 | 16.8 | 2.1
Functional Analysis | Analysis | 10 | 1.25 | 2 | 0.25 | 12 | 1.5 | 12 | 1.5 | Mike 5h John 5h
Solution Document | Analysis | 4 | 0.5 | 0.8 | 0.1 | 4.8 | 0.6 | 4.8 | 0.6
Development | Development | 30 | 3.75 | 6 | 0.75 | 36 | 4.5 | 36 | 4.5
Backend | Development | 20 | 2.5 | 4 | 0.5 | 24 | 3 | 24 | 3 | New API
Frontend | Development | 10 | 1.25 | 2 | 0.25 | 12 | 1.5 | 12 | 1.5 | New buttons
Test | Test | 10 | 1.25 | 2 | 0.25 | 12 | 1.5 | 12 | 1.5
Validation | Validation | 5 | 0.625 | 1 | 0.125 | 6 | 0.75 | 6 | 0.75
Release and monitoring | Release | 20 | 2.5 | 4 | 0.5 | 24 | 3 | 24 | 3
Overhead | Analysis | 23.7 | 2.9625 | 0 | 0 | 23.7 | 2.9625 | 23.7 | 2.9625 | Project Management
Total base (h) | 102.7 | Total base (D) | 12.8375
Total CTG (h) | 15.8 | Total CTG (D) | 1.975
Total with CTG (h) | 118.5 | Total with CTG (D) | 14.8125
Total presented (h) | 118.5 | Total presented (D) | 14.8125